# International Grading Agency (IGA) System Development

## Phase 1 - Complete Quotation & Implementation Timeline

Project Value: 40,000 EGP
Duration: 4 Weeks (28 Days)
Delivery Model: Fixed-Scope with Weekly Milestones
Developer: Mustafa Nazier
Date: December 25, 2025

## Executive Summary

This document outlines the complete development plan for Phase 1 of the International Grading Agency (IGA) grading and certification system. The project will deliver a production-ready, audit-compliant platform built on ERPNext as the operational backbone, with a secure API integration layer connecting to a public-facing website.

Phase 1 delivers: - Complete ERPNext implementation with custom IGA application - Role-Based Access Control (RBAC) with separation of duties - End-to-end submission and grading workflows - Structured grading system with audit trails - Imaging and digital archiving - Invoicing and inventory management - Public website with verification and tracking - Secure REST API with authentication and rate limiting

## Project Scope - Phase 1

### Core Deliverables

#### 1. ERPNext Core Operational Backbone

- Fresh ERPNext installation and configuration

- Custom IGA application development

- Database schema design and implementation

- System configuration and optimization

#### 2. Roles, Permissions & Governance

- Implementation of RBAC system

- User role definitions (Admin, Grader, QC Officer, Imaging Operator, Finance, Operations)

- Separation of duties enforcement

- Permission matrix implementation

#### 3. Submissions Intake & End-to-End Tracking

- Customer onboarding workflow

- Submission creation and intake process

- Status tracking system

- Communication notifications

#### 4. Structured Grading Inputs & Grade Calculation

- Master coin reference data management

- Coin instance creation

- Grading input forms (structured)

- Automated grade calculation engine

- Prohibition of manual grade entry

#### 5. Grade Approval, Locking & Overrides

- Multi-level approval workflow

- Grade locking mechanism

- Override authorization system with justification

- Complete audit trail for all actions

- Historical data preservation

#### 6. Imaging & Digital Archiving

- Image upload and management system

- Metadata tagging and linking to coin instances

- Image storage optimization

- Quality control for images

#### 7. Invoicing & Basic Finance Records

- Automated invoice generation

- Payment tracking

- Basic financial reporting

- Integration with ERPNext Accounting module

#### 8. Inventory of Consumables & Basic Stock Control

- Slab and label inventory management

- Stock level tracking

- Reorder point notifications

- Usage logging per certification

#### 9. Shipping / Fulfillment Status Management

- Shipping status workflow

- Carrier integration preparation

- Tracking number management

- Customer notification system

#### 10. Public Website

- Informational pages (About, Services, Contact)

- Submission guidance pages

- Certification verification tool (by cert number)

- Customer submission status tracking

- Responsive design for mobile and desktop

#### 11. Secure API Integration Layer

- RESTful API development

- JWT-based authentication

- Request logging and audit trails

- Rate limiting implementation (100 requests/hour per user)

- API documentation with Swagger/OpenAPI

- Error handling and validation

## Technology Stack

### Backend

- ERPNext: Version 15.x (Latest Stable)

- Frappe Framework: Version 15.x

- Database: MariaDB 10.6+

- Server: Ubuntu 22.04 LTS

- Python: 3.10+

- API Framework: Frappe REST API + Custom endpoints

### Frontend (Website)

- Framework: To be provided by client’s frontend developer

- API Integration: RESTful consumption

- Authentication: JWT tokens

### Infrastructure

- Hosting: VPS or Cloud (AWS/DigitalOcean/Client’s choice)

- Web Server: Nginx

- SSL: Let’s Encrypt

- Backup: Automated daily backups

### Development Tools

- Version Control: Git/GitHub

- Documentation: Markdown + Swagger

- Testing: Frappe Test Framework

## Financial Breakdown

### Total Project Cost: 40,000 EGP

#### Cost Allocation by Task Category

| Category | Tasks | Budget (EGP) | % of Total |
| --- | --- | --- | --- |
| Week 1: Infrastructure & Foundation | Environment setup, ERPNext installation, initial configuration | 8,000 | 20% |
| Week 2: Core Application Development | Custom doctypes, workflows, grading system, RBAC | 12,000 | 30% |
| Week 3: Advanced Features & Integration | API development, imaging system, inventory, invoicing | 12,000 | 30% |
| Week 4: Website Integration & Testing | API finalization, documentation, testing, deployment | 8,000 | 20% |

#### Detailed Task Breakdown with Budget

Week 1: Infrastructure & Foundation (8,000 EGP) - Server provisioning and configuration: 1,200 EGP - ERPNext installation and initial setup: 1,500 EGP - Database configuration and optimization: 1,000 EGP - Custom IGA app scaffolding: 1,500 EGP - Version control setup: 500 EGP - Development environment configuration: 800 EGP - Documentation framework setup: 500 EGP - Security hardening (firewall, SSL): 1,000 EGP

Week 2: Core Application Development (12,000 EGP) - Master data doctypes (Coin Types, Designations): 1,500 EGP - Customer and Submission doctypes: 2,000 EGP - Coin Instance and Certification Number system: 2,500 EGP - Grading input forms and calculation engine: 3,000 EGP - RBAC implementation (roles, permissions): 1,500 EGP - Workflow automation (submission intake): 1,000 EGP - Email notification system: 500 EGP

Week 3: Advanced Features & Integration (12,000 EGP) - Grade approval and locking mechanism: 2,000 EGP - Override system with audit trail: 1,500 EGP - Imaging system development: 2,500 EGP - API endpoint development (auth, submissions, verification): 3,000 EGP - Inventory management (slabs/labels): 1,500 EGP - Invoicing automation: 1,000 EGP - Shipping management: 500 EGP

Week 4: Website Integration & Testing (8,000 EGP) - API documentation (Swagger/OpenAPI): 1,000 EGP - Rate limiting and security hardening: 1,500 EGP - Frontend developer support and integration: 2,000 EGP - Comprehensive testing (functional, security, RBAC): 2,000 EGP - User acceptance testing support: 500 EGP - Deployment and go-live: 500 EGP - Handover documentation: 500 EGP

## Implementation Timeline - 4 Weeks

### Week 1: Foundation & Infrastructure Setup

Days 1-7 | Budget: 8,000 EGP

#### Day 1-2: Environment Provisioning

- ☐ Server provisioning (VPS/Cloud setup)

- ☐ Ubuntu 22.04 LTS installation and configuration

- ☐ Firewall configuration (UFW)

- ☐ SSH key-based authentication setup

- ☐ Basic security hardening

- Deliverable: Secure server environment ready for ERPNext

#### Day 3-4: ERPNext Installation

- ☐ Install required dependencies (Python, Node.js, MariaDB, Redis)

- ☐ Frappe bench installation

- ☐ ERPNext installation via bench

- ☐ Site creation and initial configuration

- ☐ Administrator account setup

- ☐ SSL certificate installation (Let’s Encrypt)

- ☐ Nginx configuration for production

- Deliverable: Fully functional ERPNext instance accessible via HTTPS

#### Day 5: Database & Performance Configuration

- ☐ MariaDB optimization for production

- ☐ Database backup strategy implementation

- ☐ Redis cache configuration

- ☐ Performance monitoring setup

- ☐ Log rotation configuration

- Deliverable: Optimized database and caching layer

#### Day 6-7: Custom IGA Application Scaffolding

- ☐ Create custom Frappe app: iga_grading

- ☐ Define module structure

- ☐ Configure hooks.py for custom behavior

- ☐ Setup version control (Git repository)

- ☐ Create development branch strategy

- ☐ Initial documentation structure (README, CONTRIBUTING)

- Deliverable: IGA custom app framework with version control

Week 1 Milestone Payment: 8,000 EGP
Acceptance Criteria: ERPNext running on secure server with custom IGA app initialized

### Week 2: Core Application Development

Days 8-14 | Budget: 12,000 EGP

#### Day 8-9: Master Data Doctypes

- ☐ Create Coin Type doctype (denomination, country, year, series)

- ☐ Create Designation doctype (MS, PR, PF, etc.)

- ☐ Create Grade Scale doctype (1-70 scale)

- ☐ Create Label Template doctype

- ☐ Setup reference data relationships

- ☐ Implement data validation rules

- ☐ Create import templates for bulk data entry

- Deliverable: Complete master data structure

#### Day 10-11: Customer & Submission Management

- ☐ Customer doctype enhancement (collector/dealer designation)

- ☐ Submission doctype with intake workflow

- ☐ Submission Item child table

- ☐ Status tracking (Received, In Grading, QC, Complete)

- ☐ Auto-numbering for submission IDs

- ☐ Email notification triggers

- Deliverable: Functional submission intake system

#### Day 12: Coin Instance & Certification System

- ☐ Coin Instance doctype (individual coin record)

- ☐ Permanent Certification Number generation (unique, immutable)

- ☐ Lineage tracking fields (for regrades)

- ☐ Metadata fields (slab ID, label variant)

- ☐ Population counter integration

- ☐ Certification PDF template

- Deliverable: Core certification infrastructure

#### Day 13: Grading Input System

- ☐ Grading Input doctype (strike, surface, luster, eye appeal)

- ☐ Grading criteria configuration

- ☐ Grade calculation formula implementation

- ☐ Prohibition of manual grade entry (validation)

- ☐ Grading notes and comments system

- ☐ Grader assignment logic

- Deliverable: Structured grading system with automatic calculation

#### Day 14: RBAC Implementation

- ☐ Define custom roles:

  - System Administrator

  - Grader

  - Quality Control Officer

  - Imaging Operator

  - Finance Officer

  - Operations/Shipping Officer

- ☐ Configure role permissions for each doctype

- ☐ Implement separation of duties rules

- ☐ User role assignment workflow

- ☐ Permission validation testing

- Deliverable: Complete RBAC system with separation of duties

Week 2 Milestone Payment: 12,000 EGP
Acceptance Criteria: All core doctypes operational with RBAC enforced

### Week 3: Advanced Features & API Development

Days 15-21 | Budget: 12,000 EGP

#### Day 15-16: Grade Approval & Locking System

- ☐ Grade approval workflow (multi-level)

- ☐ Quality Control review process

- ☐ Grade locking mechanism (make record read-only)

- ☐ Override authorization system

- ☐ Override justification requirement (mandatory text field)

- ☐ Audit log for all grading actions

- ☐ Historical data preservation (version control)

- ☐ Email notifications for approvals

- Deliverable: Complete approval workflow with audit trail

#### Day 17: Imaging & Digital Archiving

- ☐ Image Upload doctype

- ☐ Image-to-Coin Instance linking

- ☐ Metadata tagging (obverse/reverse, angles)

- ☐ Image quality validation

- ☐ Thumbnail generation

- ☐ Storage optimization (compression)

- ☐ Image viewer integration

- ☐ Imaging operator workflow

- Deliverable: Complete imaging system with quality control

#### Day 18-19: API Development - Core Endpoints

- ☐ Setup Frappe REST API framework

- ☐ Implement JWT authentication

- ☐ Create API endpoints:

  - /api/auth/login - User authentication

  - /api/auth/validate - Token validation

  - /api/submissions/create - New submission

  - /api/submissions/{id} - Submission details

  - /api/submissions/list - User’s submissions

  - /api/coin/{cert_number} - Coin verification

  - /api/coin/{cert_number}/images - Coin images

- ☐ Request/response validation

- ☐ Error handling implementation

- ☐ API logging system

- Deliverable: Functional REST API with authentication

#### Day 20: Inventory & Invoicing

- ☐ Consumables doctype (slabs, labels, holders)

- ☐ Stock level tracking

- ☐ Reorder point notifications

- ☐ Usage logging per certification

- ☐ Invoice generation automation

- ☐ Link submissions to invoices

- ☐ Payment status tracking

- ☐ Basic financial reporting

- Deliverable: Inventory and invoicing systems operational

#### Day 21: Shipping Management

- ☐ Shipping Status doctype

- ☐ Fulfillment workflow

- ☐ Tracking number assignment

- ☐ Carrier selection

- ☐ Customer notification on shipment

- ☐ Delivery confirmation

- Deliverable: Complete shipping workflow

Week 3 Milestone Payment: 12,000 EGP
Acceptance Criteria: All features operational with API endpoints functional

### Week 4: Integration, Testing & Deployment

Days 22-28 | Budget: 8,000 EGP

#### Day 22: API Security & Rate Limiting

- ☐ Implement rate limiting (100 requests/hour per user)

- ☐ Setup Redis for rate limit storage

- ☐ IP-based blocking for abuse

- ☐ CORS configuration

- ☐ API key management for frontend

- ☐ Security headers configuration

- ☐ SQL injection prevention validation

- Deliverable: Production-grade API security

#### Day 23: API Documentation

- ☐ Generate Swagger/OpenAPI specification

- ☐ Write API endpoint descriptions

- ☐ Provide request/response examples

- ☐ Authentication flow documentation

- ☐ Error code reference

- ☐ Rate limit documentation

- ☐ Integration guide for frontend developer

- Deliverable: Complete API documentation

#### Day 24: Frontend Developer Support

- ☐ Provide API credentials and base URL

- ☐ Support integration testing

- ☐ Debug authentication issues

- ☐ Verify data flow between website and ERPNext

- ☐ Test certification verification on website

- ☐ Test submission status tracking

- Deliverable: Successful frontend-API integration

#### Day 25-26: Comprehensive Testing

- ☐ Functional testing of all workflows

- ☐ RBAC permission validation (test each role)

- ☐ Grading calculation accuracy testing

- ☐ Audit trail verification

- ☐ Override system testing

- ☐ API endpoint testing (Postman collection)

- ☐ Security testing (authentication, authorization)

- ☐ Performance testing (load testing)

- ☐ Data integrity validation

- ☐ Backup and restore testing

- Deliverable: Test report with all issues resolved

#### Day 27: User Acceptance Testing (UAT)

- ☐ Prepare UAT environment

- ☐ Create test scenarios and scripts

- ☐ Conduct UAT sessions with client

- ☐ Document feedback and issues

- ☐ Implement critical fixes

- ☐ Re-test after fixes

- Deliverable: UAT sign-off document

#### Day 28: Deployment & Handover

- ☐ Production deployment

- ☐ Database migration verification

- ☐ Performance monitoring setup

- ☐ Backup verification

- ☐ Create system administrator guide

- ☐ Create user role manuals (per role)

- ☐ Provide operational procedures document

- ☐ Handover credentials (server, database, ERPNext)

- ☐ Remove developer access

- ☐ Final project documentation delivery

- Deliverable: Production system with complete documentation

Week 4 Milestone Payment: 8,000 EGP
Acceptance Criteria: System live in production with full documentation delivered

## Deliverables Checklist

### Software Deliverables

- ☐ ERPNext production instance with IGA custom app

- ☐ All custom doctypes and workflows

- ☐ REST API with full functionality

- ☐ Database with initial configuration

- ☐ SSL-secured web access

### Documentation Deliverables

- ☐ System Architecture Document

- ☐ Database Schema Documentation

- ☐ API Documentation (Swagger/OpenAPI)

- ☐ User Manuals (per role):

  - System Administrator Guide

  - Grader User Guide

  - QC Officer Guide

  - Imaging Operator Guide

  - Finance Officer Guide

  - Operations/Shipping Guide

- ☐ ERPNext Customization Guide

- ☐ Deployment and Environment Guide

- ☐ Security and Backup Procedures

- ☐ Troubleshooting Guide

### Access & Credentials

- ☐ Server SSH credentials

- ☐ Database root credentials

- ☐ ERPNext Administrator credentials

- ☐ API authentication keys

- ☐ Git repository access

- ☐ All credentials documented in secure handover document

## Payment Schedule

| Milestone | Deliverables | Amount (EGP) | Due Date |
| --- | --- | --- | --- |
| Milestone 1 | Week 1 completion - Infrastructure ready with ERPNext installed | 8,000 | End of Week 1 |
| Milestone 2 | Week 2 completion - Core application with RBAC | 12,000 | End of Week 2 |
| Milestone 3 | Week 3 completion - All features and API operational | 12,000 | End of Week 3 |
| Milestone 4 | Week 4 completion - Testing, deployment, handover | 8,000 | End of Week 4 |
| Total |  | 40,000 EGP |  |

Payment Terms: - Payments due upon written acceptance of milestone deliverables - Each milestone requires client sign-off before proceeding to next - Final payment upon complete system handover and documentation delivery

## Acceptance Criteria

### Week 1 Acceptance

- ERPNext accessible via HTTPS

- Custom IGA app installed and visible

- Database optimized and backed up

- Development environment functional

### Week 2 Acceptance

- All master data tables operational

- Submission intake workflow functional

- Grading system calculating grades correctly

- RBAC enforcing separation of duties

- All roles testable with demo users

### Week 3 Acceptance

- Grade approval and locking working

- Imaging system uploading and displaying images

- All API endpoints responding correctly

- JWT authentication functional

- Inventory and invoicing generating records

### Week 4 Acceptance

- API documentation complete and accurate

- All security measures active (rate limiting, logging)

- Website successfully consuming API

- All tests passed with zero critical issues

- Complete documentation delivered

- System deployed in production

## Assumptions & Dependencies

### Client Responsibilities

- Server/Hosting: Client to provide or approve server specifications (minimum 2 vCPU, 4GB RAM, 50GB SSD)

- Domain Name: Client to provide domain for ERPNext and API

- Frontend Developer: Client’s frontend developer available for API integration starting Week 3

- Content: Client to provide:

  - Initial master data (coin types, designations)

  - Company logo and branding assets

  - Website content (text, images)

  - Terms of service and privacy policy

- Testing Participation: Client availability for UAT in Week 4

- Timely Feedback: Client to provide feedback within 24 hours of milestone delivery

### Developer Responsibilities

- Complete all deliverables as specified

- Maintain code quality and documentation standards

- Provide support during frontend integration

- Ensure security best practices

- Deliver on schedule

### Exclusions (Not Included in Phase 1)

- Population/Census advanced features (Phase 2)

- Regrade lineage advanced views (Phase 2)

- Dealer/Collector advanced portals (Phase 2)

- Collector Registry (Phase 2)

- Advanced reporting and dashboards (Phase 2)

- Mobile application development

- Content creation for website

- Ongoing maintenance after handover (separate contract)

## Risk Management

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| ERPNext version compatibility issues | Low | Medium | Use latest stable version, test upgrades in dev environment |
| API integration delays | Medium | High | Start API development early, provide comprehensive documentation |
| Scope creep | Medium | High | Formal change request process, clear exclusions documented |
| Frontend developer availability | Medium | Medium | Clear API documentation, test endpoints independently |
| Data migration complexity | Low | Medium | Start with clean database, import templates for bulk data |
| Performance issues | Low | Medium | Load testing, database optimization, caching strategy |
| Security vulnerabilities | Low | High | Security testing, follow OWASP guidelines, regular updates |

## Change Management

Any changes to the agreed scope must follow this process:

- Change Request: Client submits written change request with detailed description

- Impact Analysis: Developer evaluates impact on timeline and budget

- Quotation: Developer provides separate quotation for change

- Approval: Client approves change with adjusted timeline/budget

- Implementation: Change implemented after approval and payment terms agreed

Changes requested during development may delay original delivery timeline.

## Post-Delivery Support

### Warranty Period: 30 Days

- Bug fixes for issues present at delivery (not new feature requests)

- Critical security patches

- Configuration assistance

- Documentation clarifications

### Ongoing Support (Separate Contract)

After 30-day warranty, ongoing support available at: - Monthly Retainer: 3,000 EGP/month (includes 10 hours support) - Hourly Rate: 400 EGP/hour (for ad-hoc requests) - Phase 2 Development: Separate quotation upon request

## Technical Specifications

### Server Requirements (Minimum)

- CPU: 2 vCPU cores

- RAM: 4 GB (8 GB recommended)

- Storage: 50 GB SSD (100 GB recommended)

- OS: Ubuntu 22.04 LTS

- Network: 100 Mbps bandwidth

### Software Versions

- ERPNext: 15.x (latest stable)

- Frappe: 15.x

- Python: 3.10+

- MariaDB: 10.6+

- Node.js: 18.x LTS

- Redis: 7.x

- Nginx: Latest stable

### API Specifications

- Protocol: HTTPS only

- Format: JSON

- Authentication: JWT (JSON Web Tokens)

- Rate Limit: 100 requests/hour per authenticated user

- Versioning: /api/v1/ prefix for future compatibility

### Security Standards

- TLS 1.2+ encryption

- Strong password requirements (min 12 chars, complexity rules)

- Session timeout: 24 hours

- Failed login lockout: 5 attempts

- All sensitive data encrypted at rest

- Audit logs immutable and retained for 7 years

- Regular automated backups (daily, retained 30 days)

## Appendix A: API Endpoint Reference

### Authentication Endpoints

- POST /api/auth/login - User login

- POST /api/auth/logout - User logout

- GET /api/auth/validate - Validate token

### Submission Endpoints

- POST /api/submissions - Create new submission

- GET /api/submissions/{id} - Get submission details

- GET /api/submissions - List user’s submissions

- PATCH /api/submissions/{id} - Update submission

### Coin/Certification Endpoints

- GET /api/coin/{cert_number} - Verify certification

- GET /api/coin/{cert_number}/details - Full coin details

- GET /api/coin/{cert_number}/images - Coin images

- GET /api/coin/{cert_number}/history - Grading history (if regrade)

### Invoice Endpoints

- GET /api/invoices/{id} - Get invoice (read-only)

- GET /api/invoices - List user’s invoices

### Public Endpoints (No Auth Required)

- GET /api/verify/{cert_number} - Public certification verification

- GET /api/population/{coin_type} - Population report

## Appendix B: Master Data Structure

### Coin Types Table

- Denomination (e.g., Quarter Dollar)

- Country (e.g., United States)

- Year (e.g., 1932)

- Mint Mark (e.g., S, D, P)

- Series/Type (e.g., Washington Quarter)

- Composition (e.g., Silver)

### Designations Table

- Code (e.g., MS, PF, PR)

- Full Name (e.g., Mint State, Proof)

- Description

### Grade Scale Table

- Grade Number (1-70)

- Grade Label (e.g., MS-65, PF-70)

- Description

Document Version: 1.0
Last Updated: December 25, 2025
Status: Final Proposal